## 14th August
SN | Activity | Responsible | Progress made
1 | Airtickets | Francis Makala/Rose Upor | Need details
2 | Hotel bookings for Key note speakers Wistas Inn | Philbert Komu
3 | Transportation (1 minibus, two prados from pool) | Dora Semkwiji/George Ambindwile | write letter to request transport
4 | Booking of Venues (Main library, sessions) | Dominicus Makukula | Write a letter to DVC to request waiver
5 | Refreshments (Team and Keynote Speakers) | Pili Ramadhani | Accepted 12,000 per pax
6 | Refreshments (General) | TBD
7 | Immigration processes/Letter | Rose Upor
8 | Designing of Notice of the Conference | Michael Mwakatobe
9 | Letter to Wistas for booking of venue | Rose Upor | Dr Komu to pick letter
10 | Airport Shuttle | Philbert Komu
11 | Tshirts | John Wakota
12 | Information packets | Ismail Kaminabeo
13 | Entertainment/Dance | Dominicus Makukula
14 | Designing of Identity cards | Michael Mwakatobe
15 | Design Banners (3 banners, 1 backdrop) | Michael Mwakatobe
16 | Design of Certificates of attendance | Michael Mwakatobe
17 | IT media, social media and documentation (DPS) | Ismail Kaminabeo
18 | Media booking (Mlimani media, TBC, ITV, Mwananchi, Habari leo, Azam, Daily News) | Dominicus Makukula/Isdory Jackson
19 | Booking of health team | Rose Upor | to write a letter
20 | Design and print programme | Michael Mwakatobe | Dr Karani
21 | Reception desk | Mwadawa, Neema Shadrack, Aboubakari, Alma Simba
22 | Translators/interpreters/Sign language | Isack Sondoma/Neema Ngoda
23 | Speeches | Michael Andindilile
24 | Reception Dinner/Entertainment | Gastor Mapunda/Rose Upor/Dominicus
25 | Tea Break | Daudi (Council Chamber)
26 | Press Release | Michael Karani/Isdory Jackson
27 | Ushers | Yusuf Ridhiwani | Identify 4 ushers to assist during the conference.

## 21st August
SN | Activity | Responsible | Progress made
1 | Airtickets | Francis Makala/Rose Upor | Dr Pikirayi to travel with wife. To confirm Prof Batibos ticket.
2 | Hotel bookings for Key note speakers Wistas Inn | Philbert Komu | Wistas Inn 4 nights TZS 960,000 for two rooms
3 | Transportation (1 minibus, two prados from pool) | Dora Semkwiji/George Ambindwile | Reported one vehicle confirmed (Landcruiser V8). To reserve one minibus for three days (TZS 250,000 per day = TZS 750,000)
4 | Booking of Venues (Main library, sessions) | Dominicus Makukula | To follow up with the PRO. To followup on waiver
5 | Refreshments (Team and Keynote Speakers) | Pili Ramadhani | To be discussed further.
6 | Refreshments (General) | TBD | To be discussed further.
7 | Immigration processes/Letter | Rose Upor | Dr Karani to submit list
8 | Designing of Notice of the Conference | Michael Mwakatobe | Content for the design of the
9 | Letter to Wistas for booking of venue | Rose Upor | Dr Komu to pick letter
10 | Airport Shuttle | Philbert Komu
11 | Tshirts | Dora Semkwiji | o collect information sizes and names of people
12 | Information packets | Ismail Kaminabeo/Dr. Ngwasi | Folder, brochures (undergraduate, psotgraduate), programme, notebook, pen, Identity card, evaluation form, invitation card, certificate (to provide text)
13 | Entertainment/Dance | Dominicus Makukula | To provide feedback. To write letter to HoD
14 | Designing of Identity cards | Michael Mwakatobe | To submit design and proforma
15 | Design Banners (3 banners, 1 backdrop) | Michael Mwakatobe | To submit design and proforma
16 | Design of Certificates of attendance | Michael Mwakatobe | To submit design and proforma
17 | IT media, social media and documentation (DPS) | Ismail Kaminabeo
18 | Media booking (Mlimani media, TBC, ITV, Mwananchi, Habari leo, Azam, Daily News) | Dominicus Makukula/Isdory Jackson | Approximately TZS 600,000
19 | Booking of health team | Rose Upor | Waiting for a response from Medical Officer in Charge
20 | Design and print programme | Michael Mwakatobe | Dr Karani
21 | Reception desk | Mwadawa, Neema Shadrack, Aboubakari, Alma Simba | To work on logistics of handling presenters and attendance
22 | Translators/interpreters/Sign language | Isack Sondoma/Neema Ngoda | To follow-up ( Mr Kushoka)
23 | Speeches | Michael Andindilile | To follow-up
24 | Reception Dinner/Entertainment | Gastor Mapunda/Rose Upor/Dominicus | Booking of tents (2)
25 | Tea Break | Daudi (Council Chamber)
26 | Press Release | Michael Karani/Isdory Jackson/Wakota/Kuhenga | Sunday, 10th September 2023
27 | Ushers | Yusuf Ridhiwani | Identify 4 ushers to assist during the conference.
28 | Conference bags | Dora Semkwiji
29 | Sponsor marketing strategy |  | Banners, brochures, WCF, ATCL, BASATA
30 | Website | Ismail Kaminambeo
31 | Master of Ceremony
32 | Eating area | Dora Semkwiji